## Slide 2
Project Overview
City Manager
Thomas A. Golden, Jr.

## Slide 3: Construction Update

## Slide 4: Phase 1 Construction Update

## Slide 5
    Remaining Phase 1 Activities
    Finish Bleacher Installation
    Place Loading Dock Concrete Pad
    Final Paving
    Fall Plantings
    Complete “Punchlist”

## Slide 6: Phase 2 Construction Update

## Slide 7: FALL ‘ 22
CONSTRUCTION
FENCE
DEMO EXISTING GYMNASIUM
DEMO PORTION OF EXISTING 1980 BUILDING
COMPLETED NEW GYMNASIUM BUILDING
EXISTING 1980 BUILDING
EXISTING FRESHMAN ACADEMY BUILDING
EXISTING 1922 BUILDING
LEE STREET
ARCAND DRIVE
FATHER MORISSETTE BLVD
KIRK STREET
PAIGE STREET
IMA
RR ME
CK CANAL
FRENCH STREET
TEMPORARY
MAIN ENTRY
DEMO S. BRIDGE
Phase 2 Milestones
    September 2022
    Continue Bulk Demolition
    Continue Debris Load-out
    Take down Field House
    October 2022
    Mobilize Sitework Contractor
    Demo Existing Foundation
    Remove South Bridge
    Begin Pre-excavation
    Begin Ground improvements
    November 2022
    Mobilize Concrete Contractor
    Excavate Foundations
    Form & Pour Concrete Foundations
    Install Infiltration System

## Slide 8
Demo Activities from Father Morissette

## Slide 9
Take-down 1980’s Building South End

## Slide 10
1980’s Building South End

## Slide 11: High School Campus Logistics

## Slide 12
Phase 2 – Traffic Management Plan

## Slide 13: Part 3: MBE/WBE and Workforce Progress

## Slide 14: MBE/WBE and Workforce Participation Comparison*
Total Construction Lowell Resident
10.7% of all workers (73 workers & 18,059 hours)
Total Construction
Female Workforce
is at 3.6% of all workers, (47 workers & 6,028 hours)
Total Construction
Minority Workforce
is at 25.1% of workers (313 workers & 42,477 hours)
Total MBE/WBE Contracts Awarded
$21,617,266
*Updated August 11, 2022

## Slide 15: Part 4: Designer Update

## Slide 16: Part 5: Budget

## Slide 19: Part 6: Next Steps

## Slide 20: Thank you