## Slide 2
Project Overview
City Manager
Thomas A. Golden, Jr.

## Slide 3: Phase 2 Construction Update

## Slide 4
CONSTRUCTION
FENCE
DEMO EXISTING GYMNASIUM
DEMO PORTION OF EXISTING 1980 BUILDING
COMPLETED NEW GYMNASIUM BUILDING
EXISTING 1980 BUILDING
EXISTING FRESHMAN ACADEMY BUILDING
EXISTING 1922 BUILDING
LEE STREET
ARCAND DRIVE
FATHER MORISSETTE BLVD
KIRK STREET
PAIGE STREET
IMA
RR ME
CK CANAL
FRENCH STREET
TEMPORARY
MAIN ENTRY
DEMO S. BRIDGE
Phase 2 Milestones
    January 2023
    Begin Structural Steel
    Begin Underground MEPs
    Complete Concrete Foundations at F Building/NC
    Complete Micropiles at Bridge
    February 2023
    Continue Structural Steel
    Continue Concrete Foundations at D Building
    March 2023
    Begin Concrete Slab Placements

## Slide 5
Foundation Walls (F Building & North Connector)

## Slide 6
Foundation Walls & Dampproofing (F Building)

## Slide 7
Steel Erection (North Connector)

## Slide 8
Phase 2 Structural Steel
Locus Plan
South Bridge
D Building
N. Connector
F Building
Canopy

## Slide 9: Part 3: MBE/WBE and Workforce Progress

## Slide 10: MBE/WBE and Workforce Participation Comparison*
Total Construction Lowell Resident
10.8% of all workers (87 workers & 21,198 hours)
Total Construction
Female Workforce
is at 3.6% of all workers (60 workers & 7,121 hours)
Total Construction
Minority Workforce
is at 25.2% of workers (387 workers & 49,510 hours)
Total MBE/WBE Contracts Awarded
$21,617,266
* Updated December 9, 2022

## Slide 11: Part 4: Designer Update

## Slide 12: Part 5: Budget

## Slide 15: Part 6: Next Steps

## Slide 16: Thank you